## issues
p | Column1.title | Column1.user.login | Column1.labels.name | Column1.state | Column1.milestone.title | Column1.created_at
1 | First step in refactoring code to change name to FRESCO and add new logo | drucinski |  | closed |  | 2020-08-20T14:07:17Z
2 | Convert VB6 components to C# | tslawecki | General Requirement | open | FRESCO v 1.0 | 2020-12-17T13:31:50Z
3 | Incorporate TREECS Arctic capabilities and C# ASAPP UI | tslawecki | General Requirement | open | FRESCO v 1.0 | 2020-12-17T13:32:38Z
4 | Conduct RMF certification | tslawecki | General Requirement | open | FRESCO v 2.0 | 2020-12-17T13:33:15Z
5 | Review code dependencies and refresh, remove, or leave alone as needed | tslawecki | General Requirement | open | FRESCO v 1.0 | 2020-12-17T13:34:07Z
6 | Repair all TREECS-related web links | tslawecki | General Requirement | open | FRESCO v 0.1 | 2020-12-17T13:34:25Z
7 | Build FRESCO 1.0 install package | tslawecki |  | open | FRESCO v 1.0 | 2020-12-17T14:06:45Z
8 | Build and test FRESCO 0.1 install package | tslawecki |  | closed | FRESCO v 0.1 | 2020-12-17T14:07:32Z
9 | Enter General Requirements | tslawecki | Project Management | closed |  | 2020-12-23T14:11:53Z
10 | Enter Capability Requirements | tslawecki | Project Management | closed | FRESCO v 1.0 | 2020-12-23T14:18:10Z
11 | Refresh ORNL RAIS database values (CR 1A) | tslawecki | Capability Requirement | open | FRESCO v 2.0 | 2020-12-23T14:23:14Z
12 | Create FRESCO repository based on FRESCO branch | tslawecki | Project Management | open | FRESCO v 0.1 | 2020-12-23T14:30:03Z
13 | Web update for Constituent Properties Database (CR 1B) | tslawecki | Capability Requirement | open | FRESCO v 2.0 | 2020-12-23T14:32:22Z
14 | Add Requirements Document ID to issues | tslawecki | Project Management | open |  | 2020-12-23T14:34:28Z
15 | Health Benchmarks Database (CR 2) | tslawecki | Capability Requirement | open | FRESCO v 2.0 | 2020-12-23T16:23:55Z
16 | New folk add an issue | tslawecki | Project Management | open | FRESCO v 0.1 | 2020-12-23T18:01:06Z
16 | New folk add an issue | tslawecki | bug | open | FRESCO v 0.1 | 2020-12-23T18:01:06Z
17 | Updated help file link testing | scottchinz | documentation | closed | FRESCO v 1.0 | 2020-12-23T18:08:26Z
18 | Merry Christmas | rdel1jlr |  | open |  | 2020-12-23T18:20:49Z
19 | Revise Arctic Info help document | MarkDortch | documentation | open | FRESCO v 1.0 | 2020-12-23T18:26:28Z
20 | Convert the three TREECS Tier 2 | Spiers-Circle | Capability Requirement | open | FRESCO v 1.0 | 2020-12-23T18:41:39Z
21 | Modify the MEPAS Aquifer model | Spiers-Circle | Capability Requirement | open | FRESCO v 2.0 | 2020-12-23T18:43:06Z
22 | Allow background and initial aquifer concentrations | Spiers-Circle | Capability Requirement | open | FRESCO v 1.0 | 2020-12-23T18:44:27Z
23 | Implement new logo | Spiers-Circle | Functionality | closed | FRESCO v 1.0 | 2020-12-24T15:07:50Z
24 | Move the Hydro-geo-chemical toolkit | Spiers-Circle | Functionality | closed | FRESCO v 1.0 | 2020-12-24T15:09:00Z
25 | Modify HGCT per details in the Word document | Spiers-Circle | Functionality | closed |  | 2020-12-24T15:09:57Z
26 | Modify the main FRESCO UI | Spiers-Circle | Functionality | closed | FRESCO v 1.0 | 2020-12-24T15:10:48Z
27 | Modify the Tools menu screen | Spiers-Circle | Functionality | open | FRESCO v 1.0 | 2020-12-24T15:11:59Z
28 | Modifying DES file descriptions, was "Consider renaming some modules" | Spiers-Circle | Functionality | open | FRESCO v 1.0 | 2020-12-24T15:12:50Z
29 | Develop meteorology data pre-processor (MDP). | Spiers-Circle | Functionality | open | FRESCO v 2.0 | 2020-12-24T15:13:32Z
30 | Develop a soil characterization pre-processing tool (SCPT | Spiers-Circle | Functionality | open | FRESCO v 2.0 | 2020-12-24T15:23:34Z
31 | Investigate what the MEPAS Human Receptor model | Spiers-Circle | Functionality | open | FRESCO v 1.0 | 2020-12-24T15:25:46Z
32 | Update documentation and provide a new .chm | Spiers-Circle | Functionality | open | FRESCO v 2.0 | 2020-12-24T15:27:07Z
33 | Change warning at bottom | Spiers-Circle | Corrections | open | FRESCO v 1.0 | 2020-12-24T15:34:07Z
34 | Include the new updated TREECS Munitions database | Spiers-Circle | Corrections | open | FRESCO v 1.0 | 2020-12-24T15:35:30Z
35 | Add DES and .exe files | Spiers-Circle | Corrections | open | FRESCO v 1.0 | 2020-12-24T15:38:05Z
36 | Correct the problem that is preventing the MEPAS Vadose Help file from displaying | Spiers-Circle | Corrections | open | FRESCO v 1.0 | 2020-12-24T15:38:49Z
37 | Correct UI name and wording | Spiers-Circle | Corrections | open | FRESCO v 1.0 | 2020-12-24T15:39:34Z
38 | Make corrections to the WFF Aquifer Plus Operator and other Plus operators with potential problems | Spiers-Circle | Corrections | open | FRESCO v 1.0 | 2020-12-24T15:40:18Z
39 | Make changes to the munitions items | Spiers-Circle | Corrections | open | FRESCO v 1.0 | 2020-12-24T15:41:11Z
40 | Repair the Package/Unpackage tool | Spiers-Circle | Corrections | closed | FRESCO v 1.0 | 2020-12-24T15:41:52Z
41 | If no longer needed nor used, remove the Set working directory | Spiers-Circle | Corrections | closed | FRESCO v 1.0 | 2020-12-24T15:51:58Z
42 | check boxes on the Tier Analysis Selection screen for Surface Water | Spiers-Circle | Corrections | closed |  | 2020-12-24T15:52:49Z
43 | Check proper functionality of the References and Report menu items as new features are added | MarkDortch | Functionality | open | FRESCO v 2.0 | 2020-12-31T16:31:14Z
44 | Incorporate new Soils module | tslawecki |  | open | FRESCO v 1.0 | 2021-01-07T15:44:09Z
45 | Plotting hydrologic time series in Excel locks up | tslawecki | bug | open | FRESCO v 1.0 | 2021-01-07T18:01:45Z
46 | Ensure all help buttons bring up help files. | MarkDortch | Functionality | open | FRESCO v 1.0 | 2021-01-14T17:13:14Z
47 | Minor error warnings when save a .trp file in a directory with another .trp file | MarkDortch | bug | open | FRESCO v 1.0 | 2021-01-14T17:15:52Z
48 | Improve ease-of-use for inputs in fate models for Arctic applications | MarkDortch | Capability Requirement | open | FRESCO v 1.0 | 2021-01-14T17:20:34Z
49 | Grey out Save As button in FRAMES running in FRESCO | MarkDortch | Corrections | open | FRESCO v 1.0 | 2021-01-14T17:31:21Z
50 | Correct help file references - was "Change TREECS to FRESCO throughout all utilities located under Menu/Tools" | MarkDortch | Corrections | open | FRESCO v 1.0 | 2021-01-24T18:02:57Z
51 | Need to add an explanation in the Munitions Database Editor for creating a copy of the MIDAS Extract DB | MarkDortch | documentation | closed | FRESCO v 1.0 | 2021-01-26T21:29:34Z
52 | Need to add an explanation in the Constituent Database Editor for creating a copy of the FRAMES Constituent DB | MarkDortch | documentation | open | FRESCO v 1.0 | 2021-01-27T01:08:59Z
53 | Need to add an explanation in the Benchmarks Database Editor for creating a copy of the FRESCO Benchmarks DB | MarkDortch | documentation | closed | FRESCO v 1.0 | 2021-01-27T01:37:34Z
54 | WFF Surface Water and Aquifer Percent Plus Operator | MarkDortch | bug | open |  | 2021-01-30T19:38:15Z
55 | Potential bug when linking MEPAS human exposure module to the TREECS source loading/Tier 2 soil model within FRAMES. | MarkDortch | bug | open |  | 2021-02-02T00:47:59Z
56 | Potential bug associated with MEPAS source in soil model UI in FRESCO/FRAMES | MarkDortch | bug | open |  | 2021-02-02T00:53:56Z
57 | Review references and URLs in DES files | tslawecki |  | open | FRESCO v 1.0 | 2021-02-11T17:51:36Z
58 | Resurfacing SU issue? | tslawecki | bug | open | FRESCO v 1.0 | 2021-02-18T12:44:38Z
59 | Build test suites | tslawecki | General Requirement | open | FRESCO v 1.0 | 2021-02-18T12:55:49Z
60 | Facilitate bug reporting | tslawecki | General Requirement | open | FRESCO v 1.0 | 2021-02-18T12:59:39Z
61 | Help content for HGCT Met inputs | tslawecki |  | open | FRESCO v 1.0 | 2021-02-25T18:51:53Z
62 | Build AWS server to host draft website | tslawecki | General Requirement | open |  | 2021-03-04T15:43:36Z
63 | Mark up CHM images that say "TREECS" | tslawecki | documentation | open |  | 2021-03-05T17:16:44Z
64 | Remove unused components from FRESCO 1.0 | tslawecki |  | open |  | 2021-03-11T15:13:30Z
65 | Advanced Tier II/FRAMES, none of the status lights are working | htaolimno |  | closed |  | 2021-03-22T14:59:56Z
66 | xlschart printing issue | htaolimno |  | open |  | 2021-03-22T15:02:37Z
67 | Need to change to stacked tabs on UIs | htaolimno |  | closed |  | 2021-03-22T16:10:18Z
68 | Vadose model UI help file not come up | htaolimno |  | open |  | 2021-03-27T17:18:53Z
69 | S/U module UI is no longer working | MarkDortch |  | open |  | 2021-03-28T14:43:47Z
70 | Rename databases | tslawecki |  | open |  | 2021-04-15T17:12:45Z
71 | Compare 2015 FRAMES components to current FRESCO | tslawecki |  | open |  | 2021-04-15T17:21:09Z
72 | Build GitHub repository for FRESCO web page | tslawecki |  | open |  | 2021-04-21T14:00:51Z
73 | Implement new benchmark editor | tslawecki |  | open |  | 2021-04-22T15:06:45Z
74 | Tier II Soil Model GUI Help links | drucinski |  | open |  | 2021-04-28T13:20:18Z
75 | Correct Tier 2 soil model UI for source removal BMPs | MarkDortch | Corrections | open | FRESCO v 2.0 | 2021-04-29T17:52:50Z
76 | .NET FRAMES/xlschart.exe tries to open exported Excel file if Office is not installed on the machine. | htaolimno |  | open |  | 2021-04-30T13:14:31Z
77 | Main Menu Bar | tslawecki | Mark 5/17 punchlist | open |  | 2021-05-20T15:21:13Z
78 | CHM Help | tslawecki | Mark 5/17 punchlist | open |  | 2021-05-20T15:22:22Z
79 | HGCT | tslawecki | Mark 5/17 punchlist | open |  | 2021-05-20T15:24:36Z
80 | Viewers | tslawecki | Mark 5/17 punchlist | open |  | 2021-05-20T15:26:43Z
81 | S/U | tslawecki | Mark 5/17 punchlist | open |  | 2021-05-20T15:28:59Z
82 | Test Cases | tslawecki | Mark 5/17 punchlist | open |  | 2021-05-20T15:32:22Z
83 | FRAMES | tslawecki | Mark 5/17 punchlist | open |  | 2021-05-20T15:34:22Z
84 | HGCT Grid Table Tool fixes | tslawecki |  | open |  | 2021-05-20T16:10:50Z
85 | Vadose and Aquifer Model UI | tslawecki | Mark 5/17 punchlist | closed |  | 2021-05-20T16:31:18Z
85 | Vadose and Aquifer Model UI | tslawecki | bug | closed |  | 2021-05-20T16:31:18Z
86 | RECOVERY not running | tslawecki | bug | open |  | 2021-05-20T17:14:21Z
87 | RECOVERY testing issues from Mark | htaolimno |  | open |  | 2021-06-02T19:13:16Z